## Sprint Schedule
Sprint Name | Start Date | End Date | Duration (days) | Main Tasks | Category
Sprint 1 | 2026-03-16 | 2026-03-29 | 14 | Proposal preparation (Research, Requirements) | Proposal
Sprint 2 | 2026-03-30 | 2026-04-12 | 14 | Proposal preparation (Writing, Draft) | Proposal
Sprint 3 | 2026-04-13 | 2026-04-26 | 14 | Proposal finalization and submission | Proposal
Sprint 4 | 2026-04-27 | 2026-05-10 | 14 | Feature 1: AUT Login & Verification | Feature
Sprint 5 | 2026-05-11 | 2026-05-24 | 14 | Feature 3: Browse & Discovery (Home Page) | Feature
Sprint 6 | 2026-05-25 | 2026-06-19 | 26 | Feature 4: Campus Sorting & Filtering | Feature
Holiday 1 | 2026-06-20 | 2026-07-20 | 31 | Mid-year Break | Holiday
Sprint 7 | 2026-07-21 | 2026-08-03 | 14 | Feature 6: User Profile & Trust Score | Feature
Sprint 8 | 2026-08-04 | 2026-08-17 | 14 | Feature 2: Post Listing (Image Upload) + Portfolio | Feature+Portfolio
Sprint 9 | 2026-08-18 | 2026-08-24 | 7 | Feature 7: Security Rules & Testing + Portfolio | Feature+Portfolio
Holiday 2 | 2026-08-25 | 2026-09-06 | 13 | Mid-semester Break | Holiday
Sprint 10 | 2026-09-07 | 2026-09-20 | 14 | Feature 5: Chat + Team Portfolio | Feature+Portfolio
Sprint 11 | 2026-09-21 | 2026-10-04 | 14 | iOS Conversion + Reflective Report Draft | Delivery
Sprint 12 | 2026-10-05 | 2026-10-28 | 24 | Final Portfolio + Reflective Report + Poster | Delivery
Legend
Proposal | Sprints 1–3: Proposal work
Feature | Sprints 4–7: Core features
Feature+Portfolio | Sprints 8–10: Features + Team Portfolio
Holiday | Breaks (no development)
Delivery | Sprints 11–12: iOS, Report, Poster

## Gantt Chart
AUT Swap App — Project Gantt Chart (16 Mar 2026 → 28 Oct 2026)
|  | Mar 2026 |  |  | Apr 2026 |  |  |  | May 2026 |  |  |  | Jun 2026 |  |  |  |  | Jul 2026 |  |  |  | Aug 2026 |  |  |  |  | Sep 2026 |  |  |  | Oct 2026
Sprint | Main Tasks | 16/03 | 23/03 | 30/03 | 06/04 | 13/04 | 20/04 | 27/04 | 04/05 | 11/05 | 18/05 | 25/05 | 01/06 | 08/06 | 15/06 | 22/06 | 29/06 | 06/07 | 13/07 | 20/07 | 27/07 | 03/08 | 10/08 | 17/08 | 24/08 | 31/08 | 07/09 | 14/09 | 21/09 | 28/09 | 05/10 | 12/10 | 19/10 | 26/10
Sprint 1 | Proposal preparation (Research, Requirements)
Sprint 2 | Proposal preparation (Writing, Draft)
Sprint 3 | Proposal finalization and submission
Sprint 4 | Feature 1: AUT Login & Verification
Sprint 5 | Feature 3: Browse & Discovery (Home Page)
Sprint 6 | Feature 4: Campus Sorting & Filtering
Holiday 1 | Mid-year Break
Sprint 7 | Feature 6: User Profile & Trust Score
Sprint 8 | Feature 2: Post Listing (Image Upload) + Portfolio
Sprint 9 | Feature 7: Security Rules & Testing + Portfolio
Holiday 2 | Mid-semester Break
Sprint 10 | Feature 5: Chat + Team Portfolio
Sprint 11 | iOS Conversion + Reflective Report Draft
Sprint 12 | Final Portfolio + Reflective Report + Poster
Legend
Proposal | Sprints 1–3: Proposal work
Feature | Sprints 4–7: Core features
Feature+Portfolio | Sprints 8–10: Features + Team Portfolio
Holiday | Breaks (no development)
Delivery | Sprints 11–12: iOS, Report, Poster
Notes
• Sprint 1–3: Proposal preparation & submission
• Sprint 4–10: Feature development (Feature 1,3,4,6,2,7,5 — Offline Payment excluded)
• Sprint 8–12: Team Portfolio work runs in parallel
• Sprint 11: Web → iOS conversion + Reflective Report draft
• Sprint 12: Final Portfolio + Reflective Report + Poster (ends 28/10/2026)
• Holiday 1: Mid-year Break (20/06–20/07) ¦ Holiday 2: Mid-semester Break (25/08–06/09)

## Gantt Chart (Excel)
Sprint | Offset (hidden) | Duration (days) | Start Date | End Date | Main Tasks
Sprint 12 | 203 | 24 | 2026-10-05 | 2026-10-28 | Final Portfolio + Reflective Report + Poster
Sprint 11 | 189 | 14 | 2026-09-21 | 2026-10-04 | iOS Conversion + Reflective Report Draft
Sprint 10 | 175 | 14 | 2026-09-07 | 2026-09-20 | Feature 5: Chat + Team Portfolio
Holiday 2 | 162 | 13 | 2026-08-25 | 2026-09-06 | Mid-semester Break
Sprint 9 | 155 | 7 | 2026-08-18 | 2026-08-24 | Feature 7: Security Rules & Testing + Portfolio
Sprint 8 | 141 | 14 | 2026-08-04 | 2026-08-17 | Feature 2: Post Listing (Image Upload) + Portfolio
Sprint 7 | 127 | 14 | 2026-07-21 | 2026-08-03 | Feature 6: User Profile & Trust Score
Holiday 1 | 96 | 31 | 2026-06-20 | 2026-07-20 | Mid-year Break
Sprint 6 | 70 | 26 | 2026-05-25 | 2026-06-19 | Feature 4: Campus Sorting & Filtering
Sprint 5 | 56 | 14 | 2026-05-11 | 2026-05-24 | Feature 3: Browse & Discovery (Home Page)
Sprint 4 | 42 | 14 | 2026-04-27 | 2026-05-10 | Feature 1: AUT Login & Verification
Sprint 3 | 28 | 14 | 2026-04-13 | 2026-04-26 | Proposal finalization and submission
Sprint 2 | 14 | 14 | 2026-03-30 | 2026-04-12 | Proposal preparation (Writing, Draft)
Sprint 1 | 0 | 14 | 2026-03-16 | 2026-03-29 | Proposal preparation (Research, Requirements)
Tip: The coloured bars show task duration. The blank Offset series positions each bar on the timeline.