## Overview
AUT Swap (iPhone app) — 12-Sprint Skills Plan
What this plan is for
This plan helps you learn while you build the AUT Swap iPhone app. Each sprint has one app task and one learning focus. You do not build online payment. Students meet on campus and pay with cash or bank transfer.
What the app already has
• Built with Swift and SwiftUI for iPhone.
• Screens: Login, Home, Filters, Item Detail, Post Item, Messages, Chat, Profile, Trust Score.
• Data is fake for now. Nothing is saved on a real server yet.
• Still to improve later: real login, save data, upload photos, finish Profile pages, make chat and inbox stay in sync.
Learning path (simple view)
Sprint 1–3 Getting started | Research the problem. Write the proposal. Plan the work.
Sprint 4–6 Building screens | Login. Home page. Filters. Learn how screens and state work.
Sprint 7–8 Building features | Profile and Trust Score. Post an item with photos.
Sprint 9–10 Testing & chat | Safety checks. Simple tests. Chat and messages.
Sprint 11–12 Final delivery | Compare web and iPhone. Write the report. Finish portfolio and poster.
How to use this file
1. Open “12-Sprint Skills Plan”. Follow one sprint at a time.
2. Use “Skills Tracker” to mark progress: Learn → Try → Use → Show.
3. Open “Learning Tasks” for short practice ideas.
4. Keep screenshots and notes for the Team Portfolio in Sprint 8–12.
Word guide (no short forms)
• Sprint = a short work period (about two weeks).
• SwiftUI = Apple’s tool for building iPhone screens.
• View = one screen or one part of a screen.
• View Model = the code that holds screen logic and data for the View.
• Store = a shared place in the app that keeps lists (items, chat).
• State = the current data the screen shows (logged in, filters on, etc.).
• Fake data / mock data = sample data inside the app, not from a real server.
• Trust Score = a simple rating that shows if a seller seems reliable.
• Portfolio = a team document that shows your work and learning.
• Reflective Report = a personal report about what you learned and what was hard.

## 12-Sprint Skills Plan
Sprint | Dates | What you build in the app | Learning theme | Skills to learn | What to practice in the app | Done when… | What to save for Portfolio
Sprint 1 | 16/03–29/03/2026 | Proposal: research and needs | Getting started | • Learn how campus trading apps work • Write who the users are • List must-have and nice-to-have needs • Compare with Trade Me and Facebook Marketplace | • Write the path: login → browse → chat → meet on campus • Split needs into must-have and later • Explain why cash or bank transfer on campus is safer for students | You have a clear problem, user stories, and a needs list | Research notes and needs list
Sprint 2 | 30/03–12/04/2026 | Proposal: write the draft | Getting started | • Write a clear proposal • Set the project scope • List risks and how to handle them • Draw a simple app map | • Say the plan: SwiftUI screens now, real server later if needed • Draw screens from the Features folders • Note what is fake data and what must become real later | The team has reviewed a full proposal draft | Proposal draft version 1
Sprint 3 | 13/04–26/04/2026 | Finish and submit the proposal | Getting started | • Make the document ready to submit • Plan each sprint on a board • Use fair citations • Agree who does what in the team | • Lock the feature order: Login → Home → Filter → Profile → Post → Safety → Chat • Confirm: no online payment system • Put this skills plan on the sprint board | Proposal is submitted. Sprint board is ready. | Submitted proposal and Gantt chart
Sprint 4 | 27/04–10/05/2026 | Feature 1: AUT Login and student check | Building screens | • Build forms in SwiftUI • Check email and password input • Only allow AUT emails • Learn how login state is kept in the app • Add clear labels for accessibility | • Improve Login screen errors • Show Student or Staff from the email • Keep Sign Up and Forgot Password as simple buttons for now • Read how AppState signs in and signs out | Login looks good. Wrong emails show clear errors. Ready to demo. | Login screenshots and a simple login flow drawing
Sprint 5 | 11/05–24/05/2026 | Feature 3: Home page browse and find items | Building screens | • Show item cards in a grid • Add search and campus chips • Sort by nearby, latest, or price • Move from Home to Item Detail • Use the app colours in AppTheme | • Improve search and campus chips on Home • Polish item cards and the giveaway banner • Check that tapping an item opens detail • Keep spacing and colours the same across Home | Home feels quick. Search and sort change the list. | Short Home demo video and notes about the cards
Sprint 6 | 25/05–19/06/2026 | Feature 4: Campus sort and filters | Building features | • Keep filter choices in one place • Open filters in a sheet • Let users pick campus, category, and trade type • Sort the list in different ways • Make Home update when filters apply | • Finish the Filters screen • Handle empty results and Clear All • Support giveaway-only filter • Write how filters work for the portfolio | Filters work. Empty list shows a friendly message. | Filter drawing and before/after screenshots
Holiday 1 | 20/06–20/07/2026 | Mid-year break | Holiday | Rest. Optional light reading only. | • Optional: watch a short SwiftUI beginner video • Optional: sketch the My Listings page on paper | Team is rested. Optional notes are fine. | Optional learning notes
Sprint 7 | 21/07–03/08/2026 | Feature 6: Profile and Trust Score | Building features | • Build a Profile screen • Show a Trust Score and reviews • Turn “Coming soon” pages into real pages • Use a verified badge to show campus trust | • Polish Profile and Trust Score screens • Show My Listings for the current user • Link seller name on Item Detail to Trust Score • Write why trust matters for campus trading | Profile and Trust Score can be demoed. My Listings shows own items. | Short trust write-up and profile screenshots
Sprint 8 | 04/08–17/08/2026 | Feature 2: Post an item + start Portfolio | App structure | • Pick photos from the phone library • Keep photo size small • Turn form answers into an item • Add the new item to the shared list • Start the Team Portfolio story | • Improve Post Item checks (title, photos, price) • New posts show on Home straight away • Draft Portfolio outline: problem → app → tools used • Draw: Screens → View Models → Stores → Models | Post Item works. Portfolio outline is written. | App structure drawing and Post Item demo
Sprint 9 | 18/08–24/08/2026 | Feature 7: Safety rules and testing + Portfolio | Testing & safety | • Think about safety (do not trust only the screen) • Clean user input • Finish Report and Block flows • Write a simple test checklist • Try a few automatic tests if time allows • Think about privacy for photos and chat | • Finish chat report reasons • Make listing Report do something useful • Write what server safety rules would need later • Make a smoke checklist: Login, Home, Post, Chat • Add 2–3 simple tests for email check or filters if time | Report and Block work. Test checklist is done. Portfolio has a safety section. | Test checklist and safety notes
Holiday 2 | 25/08–06/09/2026 | Mid-semester break | Holiday | Optional catch-up on Portfolio writing. | • Optional: tidy Portfolio screenshots • Optional: read a beginner guide to saving data on a server | Break finished. | Optional reading notes
Sprint 10 | 07/09–20/09/2026 | Feature 5: Chat + Team Portfolio | App structure | • Learn how chat messages update • Design chat and conversation data • Keep inbox and chat thread in sync • Build Block and Report in chat • Remind users: meet on campus, pay offline | • Update Messages when a chat message is sent • Allow chat for newly posted items • Keep clear text about campus meetup and offline pay • Write the Chat section in the Team Portfolio | Chat works end to end with fake data. Portfolio mid-draft is ready. | Chat flow drawing and Portfolio feature pages
Sprint 11 | 21/09–04/10/2026 | Polish iPhone version + Reflective Report draft | Final delivery | • Compare web app and iPhone app • Explain what changed and why • Write a Reflective Report draft • List what is still fake data | • Match iPhone features to the web plan (except online payment) • Write why the iPhone app uses chat, not a shopping cart • Draft Reflective Report: went well / hard parts / skills gained • Fix the biggest bugs from earlier sprints | You can explain web vs iPhone clearly. Reflective Report draft is done. | Reflective Report draft and comparison table
Sprint 12 | 05/10–28/10/2026 | Final Portfolio + Reflective Report + Poster | Final delivery | • Design a clear poster • Practice a short demo talk • Finish all documents • Write what you would learn next | • Finish Team Portfolio with screenshots from all features • Finish Reflective Report • Poster: problem → iPhone solution → trust and campus safety • Practice a 3–5 minute demo: Login → Home → Filter → Post → Chat → Trust | Portfolio, report, and poster are submitted. Demo is practiced. | Final Portfolio, poster file, and Reflective Report
Theme colours
Getting started
Building screens
Building features
App structure
Testing & safety
Final delivery
Holiday

## Skills Tracker
Skill group | Skill | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | Goal
Product basics | Write needs and priorities | U | U | S | [9 empty] | Show
Product basics | User stories and user path | U | U | S | T | T | [5 empty] | U |  | Use
Swift and SwiftUI | Screens, state, and bindings |  |  | L | U | U | U | U | U | T | U | S | S | Show
Swift and SwiftUI | Forms and input checks |  |  | U: S; U: T; U: T; U: U; T: U; Show: Show
Swift and SwiftUI | Lists, grids, and search |  |  | U: L; U: S; U: U; U: T; U: T; Show: Show
Swift and SwiftUI | Navigation and sheets |  |  | L | T | U | U | U | U | T | U | S |  | Show
Swift and SwiftUI | Pick and show photos |  |  | U: S; T: T; S: U |  | Use
App structure | Views, View Models, and Stores |  | L | T | U | U | U | U | S | U | S | S | S | Show
App structure | Login state in the app |  | T: L; U: S; U: T; T U: U; U S: U; Use Show: Use
App structure | Design simple data models |  | L | T | T | U | U | U | U | T | U | S |  | Show
App features | Login with AUT email rules |  | T: L; T: S; T: U; S: T |  | Show
App features | Browse, filter, and sort |  | U: U; U: S; S: T |  | Show
App features | Profile and Trust Score | [11 empty] | U | Show | bar: L to S
App features | Post a listing with photos |  | U: L; U: S; T: T; S: U |  | Show
App features | Chat, messages, report, block |  | U: L; T: U; U: S; S: U |  | Show
Quality | Write a manual test checklist |  |  |  | L | T | T | T | T | S | U | U | U | Show
Quality | Simple automatic tests |  |  |  | T: L; S: U; U: T; Show: Use
Quality | Safety and privacy thinking |  | L | T | T |  |  | T | T | S | U | U | U | Show
Delivery | Team Portfolio writing | [7 empty] | U | U | U | S | S | Show
Delivery | Reflective Report |  |  |  | U: U; U: S; Show: Show
Delivery | Poster and demo talk |  |  |  | U: L; U: U; U: S; Show: Show
Next steps | How a real server login would work |  | L | L | S: T; U: T; U: U; U: U; Show: Use later
Progress key
L | Learn — first time hearing / reading it
T | Try — practice on the app with help
U | Use — put it into the sprint feature
S | Show — good enough for Portfolio or demo

## Learning Tasks
Theme | When | Short task | Where in the app | Time
Getting started | Sprint 1–3 | Write the student problem in plain words (books, dorm items, graduation clothes). | Proposal document | 3–4 hours
Getting started | Sprint 1–3 | Draw a simple map of all screens from the Features folders. | UniversitySwap / Features | 2 hours
Building screens | Sprint 4 | Practice forms. Check email format. Show clear error text. | Login screen and Login View Model | 4 hours
Building screens | Sprint 5 | Practice grids, search, and opening a detail screen. | Home screen, item card, app routes | 4 hours
Building features | Sprint 6 | Finish filters. Test empty results and Clear All. | Filters screen and filter data | During sprint
Building features | Sprint 7 | Study how apps show ratings and verified badges. | Profile and Trust Score screens | 3 hours
App structure | Sprint 8 | Learn photo picker. Limit to a few photos. Keep files smaller. | Post Item screen and View Model | 3 hours
App structure | Sprint 8–10 | Draw: Screen → View Model → Store → Model. | AppState, Listing Store, Chat Store | 2 hours
Testing & safety | Sprint 9 | Write a safety checklist: who can post, report, and block. | Chat report and listing report | 3 hours
Testing & safety | Sprint 9 | Write 2–3 small tests for email checks if you have time. | Login View Model | 3 hours
App structure | Sprint 10 | Draw the chat path: open item → open chat → send → update inbox. | Chat Store and Messages screen | 2 hours
Final delivery | Sprint 11 | Make a table: web feature vs iPhone feature. | Whole app + Reflective Report | 4 hours
Final delivery | Sprint 11–12 | Write Reflective Report in short sections: what / why it mattered / what next. | Reflective Report | 6 hours
Final delivery | Sprint 12 | Poster with three parts: problem, iPhone solution, trust and campus safety. | Poster | 6 hours
Next steps | Sprint 9–12 | Optional: read how real login and cloud data work. Do not need to build it yet. | Future AppState and Stores | optional 6 hours